# Fetal Ultrasound AI Proposal (CRISP-DM)

Group 11 (Taswira Analytics) · Oct 21, 2026 ·

## 1. Business understanding

Problem. Sub-Saharan Africa, including rural Kenya, has too few trained sonographers. Portable ultrasound devices are getting cheaper, but interpreting what they capture is still the bottleneck. As a result, complications such as malpresentation, growth restriction and placenta praevia go undetected. Blind-sweep protocols let midwives and nurses with about an hour of training acquire scans, but they still need help judging whether a sweep contains a usable, diagnostic frame.

Business objective. Extend diagnostic reach, not replace the sonographer. The tool acts as a second reader: it confirms that a usable plane was captured, and flags sweeps that need a rescan or specialist review.

Data-mining objective. Develop and evaluate a lightweight deep learning model that classifies fetal ultrasound planes and flags usable blind-sweep frames. It must be robust to the devices, sites and operator skill found in African low-resource settings, and be delivered by 12 November 2026.

Research questions

- RQ1 (cross-region shift): How well does a plane classifier pre-trained on European scans perform on African scans, before and after fine-tuning on a few African patients?

- RQ2 (novice blind sweeps): Can a model find frames usable for abdominal measurement in blind sweeps acquired by novice operators in Sierra Leone?

- RQ3 (device and site shift): How much does performance vary across ultrasound devices and countries, and which strategy best closes the gap?

- RQ4 (deployment): What recall threshold, model size and inference latency suit a screening-support tool on a low-cost device?

Stakeholders

| Stakeholder | Use of the results |
| --- | --- |
| Midwives and nurses in rural facilities | Second reader on blind sweeps; escalate flagged scans |
| County health management teams | Plan device roll-out and specialist referral workload |
| Ministry of Health, Division of Family Health | Evidence for guidelines on AI-assisted antenatal screening |
| Sonographers and radiologists at referral hospitals | Fewer unnecessary referrals; time focused on flagged cases |
| AIMIX consortium and Aga Khan University | Independent evidence on generalisation, ahead of Kenyan validation |
| Pregnant women and communities | Earlier detection and less travel, if deployed with consent and oversight |

Success criteria. Meaningful classification on at least one clinically relevant task, plus a rigorous account of where and why performance degrades. A well-measured negative or mixed result is a valid outcome. Numeric targets are in section 5.

## 2. Data understanding

Four public, de-identified datasets cover every research question. Together they hold about 17,000 labelled standard-plane images and 1,800 novice blind sweeps.

| Dataset | Origin | Contents | Labels used | Size | Answers | Licence |
| --- | --- | --- | --- | --- | --- | --- |
| FETAL_PLANES_DB | 2 hospitals, Barcelona, Spain | ~12,400 images | Abdomen, brain (3 sub-planes), femur, thorax, cervix, other; patient, machine and operator IDs | 2.1 GB | RQ1 (source), RQ3 | Public |
| African multi-centre planes | Malawi, Egypt, Uganda, Ghana, Algeria | 450 images, 120 patients | Abdomen, brain, femur, thorax | 42.8 MB | RQ1, RQ3 | CC BY 4.0 |
| Multicentre-Fetal-Biometry | 4 sites incl. UCL Hospital, 7 devices | 4,513 images, 1,904 subjects | Head, abdomen, femur; device ID | Not stated | RQ3 | CC BY-NC-SA 4.0 |
| ACOUSLIC-AI training set | 3 public health units, Sierra Leone | 300 cases × 6 blind sweeps by novices (1 hour of training), low-cost smartphone probe | Per-pixel optimal / suboptimal / background abdominal plane; abdominal circumference (mm) | 38.0 GB | RQ2, RQ4 | CC BY-NC-SA 4.0 |

Known quality issues to verify in exploration

- Small target set: only 25 patients per African country, and Uganda and Ghana have no thorax images.

- Possible overlap: the biometry collection reportedly includes a subset derived from FETAL_PLANES_DB, which would leak source images into evaluation.

- Shortcut features: burnt-in text, calipers and device overlays can let a model recognise the device or site instead of the anatomy.

- Class imbalance: most blind-sweep frames contain no usable plane.

- Undocumented layout: the African archive does not document how patient IDs are encoded.

Not used as primary data: AIMIX Kenya (more than 1,349 women; not publicly released, see CORDIS) and FPUS23 (phantom scans, not patients).

## 3. Data preparation

All preparation steps build one unified metadata table (path, dataset, site, device, patient ID, harmonised plane) and run reproducibly from raw files.

- Subset ACOUSLIC-AI. Pull about 20 cases (~2.5 GB) with a range-request script instead of the full 38 GB zip. Keep every labelled frame plus 60 background frames per case (~0.5 GB).

- Harmonise labels. Map every plane label to one shared set: abdomen, brain/head, femur, thorax, other. Maternal cervix merges into other. ACOUSLIC mask values become not usable / suboptimal / optimal.

- Audit integrity. Check resolution, contrast, sharpness and border brightness per dataset and device. Remove unreadable files.

- Remove duplicates and leakage. Use perceptual hashes to find duplicates within and across datasets. Drop any evaluation image that duplicates a Spanish training image.

- Split by patient. Every split is grouped by patient (or ACOUSLIC case), so no patient appears in both training and test. FETAL_PLANES_DB keeps its published patient-disjoint train/test split, with a grouped validation set carved from train.

- Pre-process images. Repeat the grey channel to 3 channels for ImageNet backbones, resize to 224×224, and centre-crop if overlays are found at the borders.

- Augment, ultrasound-safe. Horizontal flip only, rotation of about ±10°, small zoom and shift, brightness and contrast jitter to mimic gain settings, and multiplicative speckle noise. No vertical flips, which would put the transducer at the bottom of the image.

- Handle imbalance. Apply balanced class weights to both tasks.

## 4. Modelling

All models share one configurable builder: a pre-trained backbone, global pooling, and a dense head with dropout and L2 regularisation. Configurations are selected by validation macro-F1, not accuracy.

| Model | Purpose | Approach |
| --- | --- | --- |
| Head experiments | Choose backbone and head | EfficientNet-B0 vs MobileNetV2; head width, depth and dropout compared over short runs |
| Source plane classifier | RQ1 baseline | Train the head on FETAL_PLANES_DB, then fine-tune the top 40 backbone layers with BatchNorm frozen; keep fine-tuning only if validation improves |
| Zero-shot transfer | RQ1 | Apply the source model unchanged to each African country, restricting predictions to the planes present |
| Few-shot fine-tuning | RQ1 | Fine-tune on k = 1, 2, 4, 6 or 10 patients per country, test on that country's remaining patients, 3 repeats per k |
| Leave-one-out models | RQ3 | Fine-tune on four countries and test on the fifth; on the biometry set, hold out one device at a time |
| Blind-sweep frame model | RQ2 | Same builder with a 3-class head (not usable / suboptimal / optimal), trained on ACOUSLIC-AI frames grouped by case |

The few-shot design replicates Sendra-Balcells et al. (2023), who reported AUC above 98% with 4–6 African patients. Training runs on CPU or free GPU notebooks; epoch counts are set in one configuration cell.

## 5. Evaluation

The primary finding is the size of the performance gap between in-domain and shifted settings, not headline accuracy. Every metric is reported on patient-held-out data.

| Question | Metric | Target |
| --- | --- | --- |
| RQ1 | Macro-F1 on African planes: zero-shot vs after few-shot fine-tuning, per country | Gap reported; ≥ 0.85 after fine-tuning |
| RQ2 | Frame-level recall and precision for optimal frames; share of cases whose top-scored frame is usable | Recall ≥ 0.80 for optimal frames |
| RQ3 | Macro-F1 and per-class recall for leave-one-country-out and leave-one-device-out | No country or device with recall < 0.50 |
| RQ4 | Calibration (expected calibration error), flag rate at the chosen threshold | Flag rate 15–30% of sweeps |

Each model also gets confusion matrices, an analysis of its most frequent and most confident errors, and AUC where the task is binary. If validation shows a target is unrealistic, we will report the result against the target rather than move it.

## 6. Deployment

The capstone delivers a deployment analysis, not a clinical deployment. It asks whether the models could run on the low-cost phones and probes midwives already use.

- Threshold and workflow: set the optimal-frame threshold on validation data to reach 0.80 recall, then report what share of sweeps would be flagged for rescan or specialist review.

- Model size: export both models to TensorFlow Lite with weight quantisation. Target under 20 MB, and check accuracy after quantisation.

- Speed: measure CPU inference time per frame. Target under 200 ms.

- Safeguards: show confidence alongside every prediction, and never present a result as a diagnosis.

Deliverables

- GitHub repository: data-access scripts, preprocessing pipeline, exploration, training and evaluation notebooks, and TFLite models.

- README with setup, reproduction steps and dataset licence terms.

- Evaluation report with results by dataset, country and device.

- Executive presentation for Ministry of Health, county health teams and AIMIX partners.

- Final report covering methods, iterations, ethics and limitations.

## Timeline, risks and limitations

| Week | Dates (2026) | CRISP-DM phases | Work |
| --- | --- | --- | --- |
| 1 | 16–22 Oct | Business and data understanding | Confirm scope; download and profile the four datasets; draft label map |
| 2 | 23–29 Oct | Data preparation, modelling | Pipeline, duplicate and leakage checks, grouped splits; head experiments and source model |
| 3 | 30 Oct – 5 Nov | Modelling, evaluation | Zero-shot, few-shot and leave-one-out runs; blind-sweep model; error analysis |
| 4 | 6–12 Nov | Evaluation, deployment | Thresholds, calibration, TFLite size and latency; report, presentation, submission |

Risks and mitigations

- Compute: ACOUSLIC-AI is 38 GB. Use a 20-case stripped subset and cached arrays.

- Leakage: patient-grouped splits throughout, plus cross-dataset duplicate removal.

- Label mismatch: map to one shared plane set and report results per dataset.

- Ceiling effects: fine-tuned plane accuracy may already be high, so the shift analysis and RQ2 carry the findings.

- Licences: two datasets are non-commercial (CC BY-NC-SA). This suits academic use and is stated in the README.

Limitations. There is no Kenyan data, no abnormality labels and no prospective clinical validation. Results are evidence for African low-resource settings in general, not approval to deploy. Kenyan validation with AIMIX data is future work.

## Sources

- FETAL_PLANES_DB, Zenodo 3904280

- African fetal planes, Zenodo 7540448

- Multicentre-Fetal-Biometry (B2FIND)

- ACOUSLIC-AI challenge data and Zenodo record

- Sendra-Balcells et al., Scientific Reports 2023

- AIMIX reporting, CORDIS

Portions of this content were developed with AI assistance and reviewed by the project team.